(Supported by

Cabinet Order

No. 654 of

24 September 2009)

Corruption Prevention and Combating Programme 2009-2013

(Informative Part)

Table of Contents

Abbreviations and Designations Used	.3

Introduction	4

1. Linking of the Programme with the Government Priorities and the Supported Development Planning Documents and the Priorities Specified Therein	5

2. Objectives and Sub-objectives of the Programme	7

3. Results and Result-based Indicators of the Programme Policy	.8

4. Tasks for the Achievement of the Results of the Programme, Result-based Indicators of the Activities, Planning of the Time-table for Execution of Tasks and the Responsible Institutions	.9

5. Planning of the Allocated and Additionally Necessary Financing Corresponding to the Tasks	23

6. Procedure for Reporting and Evaluation 	.24

Abbreviations and Designations Used

MoFA – Ministry of Foreign Affairs

CIS – Construction Information System

SecP – Security Police

SDI – State Data Inspectorate

Group of States against Corruption (GRECO) of the Council of Europe

MoF – Ministry of Finance

PO – Prosecutor’s Office

MoI – Ministry of the Interior

PMB – Procurement Monitoring Bureau

CPCB – Corruption Prevention and Combating Bureau

OPLPDCA – Office for Prevention of Laundering of Proceeds Derived from Criminal Activity

OCMA – Office of Citizenship and Migration Affairs

MoRDLG – Ministry of Regional Development and Local Government

MoJ – Ministry of Justice

LSPA – Latvian School of Public Administration

SRS – State Revenue Service

SChanc – State Chancellery

SP – State Police

SBG – State Border Guard

Introduction

Chapter III of the Law on Corruption Prevention and Combating Bureau specifies the competence of the Corruption Prevention and Combating Bureau (hereinafter – CPCB) in corruption prevention and combating and in control of the fulfilment of the financing provisions of political organisations (parties) and associations thereof, including it specifies that the CPCB shall develop a national corruption prevention and combating programme and co-ordinate the co-operation of the institutions referred to therein in order to ensure the fulfilment of the programme.

Accordingly the CPCB has developed the Corruption Prevention and Combating Programme 2009-2013 (hereinafter – Programme) – a medium-term development planning document, which determines the action directions, the main tasks and the results to be achieved in the development of the corruption prevention and combating field. The Programme defines more accurately the action directions specified in the “National Guidelines for Corruption Prevention and Combating 2009-2013” (approved by Cabinet Order No 326 of 21 May 2009).

Concurrently the referred to Guidelines and this Programme continue the activities commenced in the preceding planning period (Corruption Prevention and Combating Programme 2004-2008), expanding or narrowing it in separate fields. During drawing up of the Programme problems of institutions in relation to the fulfilment of the tasks of the preceding period, as well as their recommendations for the subsequent planning period were surveyed. Majority of ministries, as well as the State Chancellery and the State Audit Office, the Latvian Association of Local and Regional Governments, Transparency International Latvia (Sabiedrība par atklātību “Delna”) have expressed their opinion on the referred to issues.

The CPCB announced the public discussion of the Programme 2009-2013 from 10 January to 10 February 2009. A notification and a draft programme were inserted on the CPCB Internet home page, an informative banner was created and a discussion theme was opened in the forum, as well as a notification regarding the public discussion was sent to the mass media. Inhabitants, public, political, professional and other organisations were invited to provide proposals in order to make the action directions and tasks specified in the draft national programme more accurate and to supplement them. In response to the announced public discussion the CPCB received the opinions of two public organisations – “Providus” and “Civic Alliance – Latvia”.

The CPCB has evaluated the necessity of further development of the tasks fulfilled, defined new tasks according to the specified action directions, as well as specified more precisely the competence of institutions, thus ensuring the succession of the policy.

Taking into account the horizontal nature of the corruption prevention and combating policy, a particular attention has been also paid to the tasks specified in other development planning documents, thus not only ensuring the linking between these policies, but also achieving expedient co-operation among institutions.

1. Linking of the Programme with the Government Priorities and the Supported Development Planning Documents and the Priorities Specified Therein

The Programme was drawn up, taking into account that specified in other documents, as well as in order to introduce the measures specified in these documents in relation to the corruption prevention and combating:

• “Operational Strategy of the Corruption Prevention and Combating Bureau 2008-2010” (Cabinet Order No. 717 of 14 November 2008). The purpose of the strategy is to make more efficient the execution of the functions and tasks specified in the Law on Corruption Prevention and Combating Bureau, as well as to ensure the implementation of the objectives specified in the development planning documents in the fields within the competence of the CPCB. The Strategy includes issues related to the execution of the functions of the CPCB, as well as the planning of human and financial resources necessary for the performance of the activities;

• “Latvian National Development Plan 2007-2013” (Cabinet Order No 564 of 4 July 2006). Sub-paragraph 4.1.4 of the Plan deals with the “Strengthening of the Capacity of Public Administration” and accordingly states that one of the tasks to be solved is “To prevent corruption in State administrative institutions” (Task No. 8);

• “Guidelines for the Development of the State Administrative Policy 2008-2013” (Cabinet Order No 305 of 3 June 2008). The Guidelines include a significant number of issues related to State administration and the efficiency of operation thereof – policy planning and financial management, corruption prevention, institutional issues, service quality, quality management, reduction of the administrative burden, development of e-government, public-private partnership, administrative proceedings, development of human resources, strengthening of the civic society and other current issues;

• Concept “Necessity of Legal Framework for Lobbying in Latvia” (Cabinet Order No. 435 of 28 July 2008). The purpose of the Concept is to allow the provision of transparency regarding taking of such national decisions, which have been drawn up within the interests of individual persons or groups. The supported alternative provides for the application of basic principles of transparency, equality and honesty to the lobbying process in the ethics codes of State and local government institutions. For the interests of the society, a public official honestly reveals, which persons have contacted the institution in order to influence the decision-making process. The public official has a duty to ensure equality in the access to information and officials to all the parties interested in reviewing the issue;

• Concept for the Financing of Political Parties (Cabinet Order No. 14 of 15 January 2009), which provides for improvement of the existing regulatory enactments, to allocate State funding to the parties for campaigns and daily expenditure, as well as to determine criminal liability, administrative liability and financial sanctions for illegal utilisation of the State funding;

• “National Programme for the Prevention, Combating and Reduction of the Organised Crime 2006-2010” (Cabinet Order No. 390 of 31 May 2006) – the purpose thereof is to make more efficient the prevention and combating of criminal offences related to the organised crime, as well as to reduce the economic impact of the organised crime, creating wholesome conditions for the fight of law enforcement institutions against the organised crime;

• operational strategies of institutions, for example, “Operational Strategy of the Ministry of Economics 2007-2009” (Cabinet Order No. 686 of 6 September 2006 (Minutes No. 43 41)) and “Development Strategy of the State Revenue Service 2007-2009” (approved by the Minister for Finance on 6 March 2007).

The recommendations of the reports of the second and the third evaluation round of the Group of States against Corruption (GRECO) of the Council of Europe have also been taken into account in development of the Programme.

Regional planning documents (development strategies) define the priority development directions, the objectives and the tasks for the achievement thereof for each region. Although they do not include a direct reference to corruption prevention, it should be noted that the horizontal nature of anti-corruption policy also marks a link with these documents. The most significant development priorities – development of human resources, development of entrepreneurship, service quality, attraction of investments etc. – and the achievement thereof is related to the spread of corruption because corruption endangers efficient achievement of the objectives specified for planning regions.

2. Objectives and Sub-objectives of the Programme

The objective of the corruption prevention and combating policy is to ensure honest and lawful use of the power entrusted to public officials within the interests of the State and the society.

The objective of the Programme is to determine the tasks, to plan the execution thereof and the funding for the implementation of the National Guidelines for Corruption Prevention and Combating 2009-2013 in order to ensure the achievement of the objective of the corruption prevention and combating policy.

In conformity with the principles specified in the guidelines “National Guidelines for Corruption Prevention and Combating 2009-2013”, the Programme is created as a complex counteraction to corruption (corruption prevention and combating, as well as education in anti-corruption issues).

Sub-objectives:

1. To improve the control of the financial operation of political parties and the associations thereof.

2. To ensure expedient and lawful action with the State and local government property, including the utilisation of the financing allocated by the European Union and other international organisations, as well as foreign states.

3. To restrict the action of public officials in situations of a conflict of interest, as well as to restrict the possibilities of public officials to legalize the illegally earned income.

4. To improve internal anti-corruption systems and to strengthen ethics in State and local government institutions, to improve the knowledge of public officials regarding the requirements for prevention of corruption.

5. To reduce the tolerance of inhabitants to corruption, to strengthen awareness of inadmissibility of corruption and the negative consequences thereof.

6. To strengthen the principle of good administration in the operation of the State and local governments.

7. To ensure timely and qualitative adjudication of matters in courts.

8. To improve the possibilities of combating criminal offences in the service of State institutions, as well as to reduce corruption in courts.

3. Results and Result-based Indicators of the Programme Policy

The results of the corruption prevention and combating policy and their indicators have been specified in the National Guidelines for Corruption Prevention and Combating 2009-2013 (approved by Cabinet Order No. 326 of 21 May 2009), and they are as follows:

| Result | Result-based Indicator | 2007 | 2010 | 2013 |
| --- | --- | --- | --- | --- |
| Public officials act lawfully and fairly in their activities and use the power and property entrusted to them only in the public interest and in an equal, expedient and lawful way | Indicator of the control of corruption (The extent, in which the power granted to officials is being used for personal benefit, is measured. The indicator includes both small-scale bribery and indicators of wide-scale corruption and State capture. In the comparative analysis of the World Bank it is expressed as a percentile rank within the context with other states) | 66 | 69 (in 2009) | 72 |
| The efficiency of investigation of criminal offences improves, thus inhabitants and public officials have an increasingly strong conviction regarding inevitability of the punishment | Indicator of the rule of law (The extent, in which individuals have a conviction and tendency to abide the public norms/legislation, including in relation to the operation of law enforcement authorities and courts, is measured) | 65.7 | 70 | 75 |
| The society at large has an increasing conviction regarding reduction of the spread of corruption in the State | Corruption perception index. (Evaluation in 10-point system where “10” means “very clean” and “0” – “highly corrupt”.) | 4.8 (in 2008 – 5.0) | 5.2 | 5.4 |

4. Tasks for the Achievement of the Results of the Programme, Result-based Indicators of the Activities, Planning of the Time-table for Execution of Tasks and the Responsible Institutions

| No | Task | Responsible institution | Term for the execution | Result of activity/result-based indicator | Link to other development planning documents (where applicable) |
| --- | --- | --- | --- | --- | --- |
| 1. Improvement of the System for Financing of Political Parties and Associations Thereof |
| 1. | To establish a regulatory basis in order to introduce State financing to political parties according to the alternative supported in the Concept for the Financing of Political Parties | MoJ CPCB | According to that specified in the Cabinet Order No. 14 of 15 January 2009, On the Concept for the Financing of Political Parties | Draft regulatory enactment(s) has (have) been submitted to the Cabinet | Concept for the Financing of Political Parties (Cabinet Order No. 14 of 15 January 2009) |
| 2. | To specify more precisely the mechanisms for the reporting of political parties and the associations thereof | MoJ CPCB | According to that specified in the Cabinet Order No. 14 of 15 January 2009, On the Concept for the Financing of Political Parties | Draft regulatory enactment(s) has (have) been submitted to the Cabinet | Concept for the Financing of Political Parties (Cabinet Order No. 14 of 15 January 2009) |
| 3. | To improve the liability for the financial violations of political parties and the associations thereof and to ensure a commensurate, efficient and deterring mechanism of sanctions, as well as adequate control processes and also the institutions involved in the supervision and control | MoJ CPCB | According to that specified in the Cabinet Order No. 14 of 15 January 2009, On the Concept for the Financing of Political Parties | Draft regulatory enactment(s) has (have) been submitted to the Cabinet | Concept for the Financing of Political Parties (Cabinet Order No. 14 of 15 January 2009) Report of the Third Evaluation Round of GRECO On Transparency of Party Funding in Latvia Guidelines for the Development of the State Administrative Policy 2008-2013 |
| 4. | To specify more precisely the regulation of the pre-electoral campaign process, defining, for example, the term “covert pre-electoral campaign” and determining a restriction to use State and local government property in campaigns | MoJ CPCB | According to that specified in the Cabinet Order No. 14 of 15 January 2009, On the Concept for the Financing of Political Parties | Draft regulatory enactment(s) has (have) been submitted to the Cabinet | Concept for the Financing of Political Parties (Cabinet Order No. 14 of 15 January 2009) Guidelines for the Development of the State Administrative Policy 2008-2013 |
| 5. | To analyse experience of electoral campaigns and to evaluate the regulation of pre-electoral campaigns and the financing system of parties | CPCB | 9 months following each election | Report on the pre-election campaign and the financing system of parties within the context of the course of pre-election campaign |  |
| 6. | Informing the society regarding the violations of the procedures for pre-electoral campaign detected in activities of political organisations and the associations thereof, as well as regarding the violations of financing provisions of political organisations and associations thereof | CPCB | Permanently | Information ensured on the CPCB home page |  |
| 7. | To develop a concept on possibilities of strengthening the independence of the Corruption Prevention and Combating Bureau, thus ensuring the introduction of that specified in Recommendation of the Council of Europe REC (2003) 4 On Common Rules Against Corruption in the Funding of Political Parties and Electoral Campaigns | CPCB | 30 November 2009 | Concept On Strengthening the Independence of the Corruption Prevention and Combating Bureau submitted to the Cabinet | Evaluation Report on Latvia On Transparency of Party Funding of the Third Evaluation Round of GRECO |
| 2. Provision of Equality and Transparency in the Lobbying Process |
| 8. | To make amendments to regulatory enactments, determining the place and extent of publishing information regarding communication of institutions and local governments with lobbyists | CPCB | According to the Cabinet Order No. 435 of 28 July 2008, On Concept “Necessity of Legal Framework for Lobbying in Latvia” | Draft regulatory enactment(s) has (have) been submitted to the Cabinet | Concept “Necessity of Legal Framework for Lobbying in Latvia” |
| 9. | To make amendments to regulatory enactments, determining that proposals for amendments to draft laws to be reviewed by the Saeima should be published in timely manner, adding a justification and information regarding consultations with private individuals, which have taken place | CPCB | According to the Cabinet Order No. 435 of 28 July 2008, On Concept “Necessity of Legal Framework for Lobbying in Latvia” | Draft regulatory enactment(s) has (have) been submitted to the Cabinet | Concept “Necessity of Legal Framework for Lobbying in Latvia” |
| 10. | To prepare and distribute information to political parties and the society regarding the difference between lobbying and corruption, the cases when lobbying may be corrupt, as well as recommendations for political parties and the representatives thereof in State institutions in relation to taking of such decisions, which concern contributors of the relevant party | CPCB | 31 March 2010 | Information ensured on the Internet – on the CPCB home page, as well as using the informative issue “Knaģis” |  |
| 3. Improvement of the Processes for Granting State and Local Government Property, as well as Financial Resources |
| 11. | To identify corruption risks in the field of delegating functions of State administration | CPCB | 31 April 2011 | Report on corruption risks when delegating State functions |  |
| 12. | To survey the practice of institutions in action involving State and local government property, identifying main problems and corruption risks, and to draw up guidelines for reduction of corruption risks | CPCB | 31 May 2010 (practice of institutions surveyed) 31 December 2010 (guidelines drawn up) | Guidelines | Operational Strategy of the Corruption Prevention and Combating Bureau 2008-2010 |
| 3.1. In the Field of Public-Private Partnership |
| 13. | To analyse the practice of institutions in the field of public-private partnership from the point of view of corruption risks | CPCB | 31 December 2013 | Report on the practice of institutions in the field of public-private partnership |  |
| 3.2. In the Field of Public Procurements |
| 14. | To conduct analysis regarding which exceptions of the procurement procedures it is necessary to draw up guidelines and to draw them up in order to promote the observation of the principle of transparency, free competition and equality | CPCB MoF PMB | 31 September 2011 | Guidelines drawn up according to the results of analysis |  |
| 15. | To evaluate the potential solutions for improvement of liability for violations in the procurement process | MoF PMB | 1 May 2010 | Concept reviewed by the Cabinet |  |
| 3.3. In Allocation of the Financing of the European Union and Other International Institutions |
| 16. | To analyse the system for the control and supervision of allocation and introduction of the EU financing and the violations detected in the time period from 2007 to 2013 | MoF CPCB | 31 June 2013 | Informative report on risks, including corruption risks, in relation to the allocation and acquisition of the financing of the European Union and other international institutions | Examination of project requests and fulfilment is provided for by the Operational Strategy of the Ministry of Finance 2007-2009 (updated for the time period 2008-2010) |
| 4. Provision of Efficient Control over the Activities of such Public Officials who are Involved in the Processes of Allocating State and Local Government Property, as well as Financial Resources |
| 17. | To ensure signing of attestations of objectivity and confidentiality as regards the officials involved in allocation of the financing of the European Union and other international institutions | MoRDLG | As necessary, organising an evaluation of the submitted projects | Regulation provides for signing of attestations of objectivity and confidentiality for the referred to officials |  |
| 18. | To draw up guidelines, determining the circle of the officials to be inspected according to corruption risks and the amount of examinations, as well as to draw up the plan of inspections | CPCB | 31 December 2009 | Guidelines drawn up |  |
| 19. | To perform random pre-planned inspections of the activities of public officials in relation to allocation of the financing of the European Union and other international institutions | CPCB | Beginning from 2010 | Number of the inspected officials | Operational Strategy of the Corruption Prevention and Combating Bureau 2008-2010 |
| 5. Control of the Activities of Public Officials in the Field of Preventing Conflicts of Interest |
| 20. | To develop a draft concept on further development of the Law On Prevention of Conflict of Interest in Activities of Public Officials | CPCB | 31 December 2009 | Draft concept submitted to the Cabinet | Operational Strategy of the Corruption Prevention and Combating Bureau 2008-2010 |
| 21. | To ensure consultations to the heads of institutions regarding prevention of conflict of interest | CPCB | Permanently | Discussions/meetings every year (at least one measure) |  |
| 22. | To draw up a concept on the potential solutions in order to ensure the publication of information regarding the administrative punishments applied to officials and the violations committed by officials, taking into account the Personal Data Protection Law | CPCB MoJ MoI | 31 December 2010 | Draft concept submitted to the Cabinet |  |
| 23. | To update information on the home page of the SRS, aggregating the most frequently asked questions and answers to them in relation to the information to be indicated in declarations of public officials | MoF VID | 1 February of each year | Current information on the home page of the SRS, explaining the filling-in of declarations of public officials |  |
| 6. Improvement of the System for Control of the Income and Property Status of Public Officials |
| 24. | To prepare an informative report to the Cabinet on the problems in relation to issues of selecting the staff of capital companies and other State and local government institutions not subordinate to the State civil service – transparency of the processes of taking the office, criteria for selection, etc. | SChanc MoF MoRDLG CPCB | 1 June 2011 | Informative report submitted to the Cabinet |  |
| 25. | To improve and expand the range of such measures, which are performed in order to efficiently identify the income of public officials, as well as to determine accurately the property status of public official, particularly at the beginning of an inspection or investigation | CPCB | 31 December 2009 | Foreign experience aggregated and recommendations developed | Report of Recommendations of the Second Evaluation Round of GRECO |
| 7. Improvement of the Internal Control Mechanisms in State and Local Government Institutions |
| 26. | To update anti-corruption plans of institutions and local governments, including to supplement them with the new tasks from this Programme | All State administrative institutions, local governments | Once a year | Anti-corruption plans of institutions and local governments updated |  |
| 27. | On the basis of the practice of institutions to develop guidelines for public officials on action in case if a bribe is offered | CPCB | 31 December 2011 | Guidelines drawn up |  |
| 28. | To update guidelines on identification of corruption risks of institutions, management and anti-corruption measures, including in cases where a corruptive violation has been detected, as well as to develop a sample anti-corruption plan or “standard” | CPCB | 31 October 2009 | Guidelines updated |  |
| 29. | To survey and analyse the practice of institutions in organising internal anti-corruption measures, introducing a regular evaluation of corruption prevention mechanisms of State institutions and local governments | CPCB | 31 December 2009 31 December 2011 | Analysis performed, regular evaluation of corruption prevention mechanisms performed by institutions introduced |  |
| 30. | To develop guidelines on internal anti-corruption measures in the police, customs and border guard | CPCB | 1 June 2010 | Guidelines drawn up | Operational Strategy of the Corruption Prevention and Combating Bureau 2008-2010 |
| 31. | Development of an ethics code for persons employed in State administration | SChanc CPCB | 30 September 2010 | Regulatory enactment “Ethics Code for Persons Employed in State Administration” drawn up | Guidelines for the Development of the State Administrative Policy 2008-2013 |
| 32. | Informing of the persons employed in State administration and of the society regarding the basic principles of ethics in State administration | SChanc CPCB | Permanently, beginning from 2010 | The number of seminars for employees of State administration on ethics and loyalty for introduction of the “Ethics Code for Persons Employed in State Administration” (3 seminars in 2009, 5 seminars in 2011, 5 seminars in 2013) | Guidelines for the Development of the State Administrative Policy 2008-2013 |
| 33. | To perform analysis on the quality of ethics codes drawn up by State institutions and local governments and to update guidelines on the development of ethics codes, including to draw up the minimum requirements for the content of an ethics code and recommendations for putting ethics codes into practice in institutions | CPCB | 1 June 2010 (analysis) 31 November 2010 (guidelines) | Guidelines drawn up |  |
| 34. | To ensure guidelines and training for tax inspectors regarding identification of signs of corruption | CPCB | 31 November 2011 | Measures directed towards increasing the level of the knowledge of tax inspectors | Report of Recommendations of the Second Evaluation Round of GRECO |
| 8. Improvement of the System for the Protection of Public Officials who Inform regarding Corruption Offences |
| 35. | Improvement of the system for the protection of persons who report on corruption violations (informers), including by introducing regulation for the protection of such public officials who inform regarding the potential conflict of interest of public officials of another relevant institution or other violations of corruption nature in the relevant institutions, as well as regarding corruption offences identified by a public official in fulfilling direct duties | CPCB (develops regulation) All State institutions, local governments (introduce) | 31 December 2009 | Draft regulatory enactment(s) has (have) been submitted to the Cabinet | Report of Recommendations of the Second Evaluation Round of GRECO Guidelines for the Development of the State Administrative Policy 2008-2013 |
| 36. | Education of employees of State and local government institutions and inhabitants on the necessity to report on violations of the law in institutions. Informing regarding witness protection programmes and the possibilities of using them, protection of providers of information and provision of anonymity | CPCB SP | Not less than once in six months | Information ensured on the Internet – on the CPCB home page, as well as using the informative issue “Knaģis” |  |
| 9. Strengthening of Awareness of Inhabitants on Inadmissibility of Corruption and Negative Consequences Thereof, Promotion of Intolerance towards Manifestations of Corruption |
| 37. | Informing the society regarding the possibilities of submitting complaints and the procedures for examination thereof | CPCB MoI SP | Permanently | Information published on the home pages of institutions |  |
| 38. | To perform educational measures and to ensure training of teachers of economics, politics and social sciences of comprehensive schools | CPCB | 31 December 2010 31 December 2011 | Two training seminars | Operational Strategy of the Corruption Prevention and Combating Bureau 2008-2010 |
| 39. | To prepare study methodological materials for pupils of comprehensive schools regarding the most important issues of anti-corruption | CPCB | 1 May 2010 | (1) manual prepared |  |
| 40. | To promote the anonymous telephone of law enforcement institutions, operation of the Internet resources for co-operation with the society | SP, SBG, SRS, CPCB, PO | Permanently | Anonymous telephone numbers are available on the Internet, published in the press, the periodical issue of the CPCB “KNAĢIS”, etc. | National Programme for the Prevention, Combating and Reduction of the Organised Crime 2006-2010 |
| 41. | Informing the society and mass media regarding the implemented anti-corruption measures and the detected cases of corruption | CPCB SRS MoI | Permanently | Informative measures |  |
| 10. Education of Public Officials in the Field of Ethics of Public Administration, Prevention of Conflict of Interest and Anti-corruption Measures |
| 42. | To ensure training of heads of institutions and responsible officials in identification of corruption risks in institutions and regarding anti-corruption organisational measures | CPCB | Permanently | At least one seminar a year | Operational Strategy of the Corruption Prevention and Combating Bureau 2008-2010 |
| 43. | To continue study programme for education of persons working in State administrative institutions and informing thereof regarding matters of ethics, issues regarding the measures for prevention of a conflict of interest and anti-corruption measures in order for these persons to train other employees of their institution | CPCB LSPA | Permanently | Study materials developed, employees of State administration trained so that they could conduct training in their institutions |  |
| 44. | To promote the electronic system for self-testing of knowledge for public officials regarding anti-corruption issues available on the CPCB home page | CPCB | Permanently | Information in the periodical issue of the CPCB “KNAĢIS” |  |
| 45. | To prepare and distribute an informative material, in electronic form, regarding the current events in the anti-corruption field to all public officials | CPCB | 4 times a year | 4 issues of the informative material “KNAĢIS” every year |  |
| 46. | To supplement the offer of study programmes for State institutions and local governments for education and informing of employees regarding issues of ethics, issues regarding the measures for prevention of a conflict of interest and anti-corruption measures in order for these persons to train other employees of their institution | CPCB | 31 June 2011 | Training modules supplemented (available on the CPCB home page). Local government employees trained | Operational Strategy of the Corruption Prevention and Combating Bureau 2008-2010 |
| 47. | On the basis of the submitted complaints on corrupt action in different State institutions and data of public surveys on institutions, which are most subjected to the risk of corruption, to organise discussions with representatives of the relevant institutions and sector in order to draw up recommendations for solving the problem | CPCB | Once a year | One discussion a year, in which recommendations for solving the problem are identified |  |
| 11. Improvement of the Quality of the Services Provided by State and Local Government Institutions, Greater Transparency and Efficient Involvement of the Society in Decision-making |
| 48. | To perform a risk evaluation in the process of application of tax exemptions and reliefs, including in relation to rebate of immovable property tax granted by local governments in accordance with Section 5, Paragraph three of the Law On Immovable Property Tax | SRS CPCB (on reliefs granted by local governments) | 31 December 2009 31 December 2010 (on reliefs granted by local governments) | Risk evaluation is taken into account in developing anti-corruption measures |  |
| 49. | To conduct an analysis of corruption risks in individual fields of licensing of entrepreneurship/issuance of permits | CPCB | 30 June 2010 | Proposals provided to responsible institutions for the prevention of corruption risks |  |
| 50. | To prepare an informative report to the Cabinet on the availability of information on home pages of institutions and the conformity thereof to the specified procedures | MoRDLG | 30 June 2010 | Informative report to the Cabinet |  |
| 51. | Establishment of electronic services so that, upon introducing remote customer service solutions, direct communication of the official and the customer could be prevented | All State administrative institutions | Permanently | Electronic services developed | Programme for the Development of Electronic Government 2005-2009 Guidelines for the Development of Information Society 2006-2013 |
| 52. | To conduct an analysis of communication of the SRS and clients thereof in order to prevent the possible risks of corruption | SRS | 31 June 2010 | Report on the results of survey of the SRS clients and efficiency of service procedures, including from the point of view of corruption risks so that measures for the prevention of corruption risks could be incorporated in the anti-corruption plan |  |
| 53. | Introduction of the Construction Information System (CIS) | MoE | 31 December 2011 | CIS established and introduced in 100% local governments by 2011 |  |
| 54. | Improvement of the Construction Information System, reviewing the construction control system and preparing proposals for improvement of the control system | MoE | 31 December 2009 | Draft regulatory enactment(s) has (have) been submitted to the Cabinet |  |
| 55. | To ensure inhabitants with access to information and communication possibilities with State and local government institutions, thus performing preventive reduction of corruption risks | All institutions and local governments | Permanently | Information regarding participation possibilities, current issues, different possibilities of communication is available and regularly updated on home pages of institutions |  |
| 56. | To simplify the procedures for fulfilment of customs and tax liabilities, to improve customer service and to reduce the direct and indirect costs of fulfilling the liabilities, concurrently ensuring the necessary control, using modern information technologies | SRS MoF | 31 December 2009 | Quick, convenient, modern and qualitative provision of services to the SRS clients ensured | Development Strategy of the State Revenue Service 2007-2009 |
| 57. | Ensuring of transparency regarding administrative processes of an institution and informing of the visitors regarding the work of the institution, ensuring that the information specified by the Cabinet is found on the home pages of institutions, including regarding the services provided thereby – samples of the documents to be submitted, the procedures for appeal of decisions and the procedures for determination of violations, for the existing working groups and contact persons thereof, etc. | MoRDLG All institutions | Permanently | Information referred to in the task available on the home pages of institutions |  |
| 58. | To draw up guidelines (to offer examples of good practice) for local governments regarding what information should be reflected on home pages of local governments | MoRDLG | 1 April 2011 | Guidelines for local governments regarding information to be inserted on the home page of a local government |  |
| 12. Improvement of the Quality of the Activities of Judges and Prevention of Corruption Risks in Court |
| 59. | Education of judges in issues of corruption prevention and ethics | CPCB Court Administration | Once a year | At least one educating measure a year |  |
| 60. | Strengthening of the principle of randomisation in the procedure for distribution of cases in courts | Court Administration MoJ | 31 December 2011 | Electronic distribution of cases ensured in all courts (development of regulation for the introduction of electronic distribution of cases in courts) |  |
| 61. | To ensure regular evaluation of the qualification and work results of judges | MoJ | 31 December 2011 | Development of regulation for the provision of regular evaluation of the qualification and work results of judges |  |
| 62. | To improve the procedures for disciplinary punishment of judges | MoJ | 31 December 2011 | Development of regulation for the improvement of the procedures for disciplinary punishment of judges |  |
| 63. | To provide proposals to the Ethics Commission of Judges according to the Bangalore Principles during the development of the Ethics Code for Judges | CPCB | 31 December 2010 | Proposals provided for improvement of the Ethics Code for Judges in order to supplement the Ethics Code for Judges accordingly |  |
| 64. | To prepare an analysis regarding corruption risks in the judicial system | CPCB | 31 December 2011 | Information included in the report on corruption risks is used for the development of anti-corruption measures in courts |  |
| 65. | To draw up proposals for anti-corruption measures in courts | CPCB | 31 December 2012 | Proposals for anti-corruption measures in courts submitted to the MoJ and the Ethics Commission of Judges |  |
| 13. Improvement of Possibilities for Detection and Proving of Criminal Offences in the Service of State Institutions, Provision of Progress of Rapid Criminal Proceedings of Good Quality |
| 66. | To conduct professional training of the staff of law enforcement institutions and raising of qualification thereof in combating economic crimes and organised crime | SP, SecP, SBG, SRS, CPCB, PO, OPLPDCA | 31 December 2010 | Creation of a training programme, training, trained employees, co-operation contacts obtained, exchange of experience taken place | National Programme for the Prevention, Combating and Reduction of the Organised Crime 2006-2010 |
| 67. | To evaluate the regulatory enactments regarding criminal liability for corruption criminal offences and trading in influence in accordance with the Criminal Law Convention On Corruption of the Council of Europe and GRECO recommendations, including to make amendments to the Criminal Law, determining liability for accepting illegal benefits, accepting offer thereof to a medical practitioner and determining liability for bribery to a medical practitioner | CPCB MoJ | 31 March 2010 | Draft concept submitted to the Cabinet | Evaluation Report on Latvia on Incriminations of the Third Evaluation Round of GRECO |
| 68. | To co-operate with the Organisation for Economic Co-operation and Development (OECD) in relation to the Convention on Combating Bribery of Foreign Public Officials in International Business Transactions of 21 November 1997 | MoFA CPCB | Permanently | Informative report on the progress of implementation of co-operation and the current situation in relation to expansion of OECD submitted to the Cabinet once a year | “Guidelines for the Co-operation of the Republic of Latvia and the Organisation for Economic Co-operation and Development (OECD)” (Cabinet Order No. 589 of 25 August 2004) |
| 69. | In order to ensure the solving of corruption prevention and combating issues within the scope of protection the financial interests of the European Union, to maintain regular and close co-operation with the European Anti-Fraud Office (OLAF), including by active participation in the OLAF training, projects supported by the OLAF, continuing participation in the network of Anti-Fraud Co-operation Services (AFCOS) | MoF, PO, MoI, CPCB | Permanently | Participation in meetings of working groups |  |
| 70. | To ensure the introduction of the Decision 2008/852/JHA of the Council of the European Union (24 October 2008) on a contact-point network against corruption | CPCB | Permanently | Participation in meetings of working groups |  |

5. Planning of the Allocated and Additionally Necessary Financing Corresponding to the Tasks

The majority of the tasks of the Programme is related to the development of different regulatory enactments and improvement of regulation, as well as development of analytical reports, guidelines and methodologies, therefore, they will be implemented within the scope of the budget granted to State institutions. The research work will be ensured by the Corruption Analysis and Policy Planning Division of the CPCB, in its turn the tasks oriented towards training and the promotion of discussions are within the competence of the Public Relations and Education Division of the CPCB, thus they conform to the operational strategy of the CPCB and are part of the functions of the CPCB divisions and additional financing is not necessary for the performance thereof.

It should be noted that the majority of informative and educating materials will be distributed in electronic form, thus not causing additional expenditure.

Due to the horizontal nature of the corruption prevention and combating policy, individual tasks were overlapping with that planned in other development planning documents. The necessary financing has also been planned in these documents and the impact of these measures on the State budget has been analysed, therefore, the costs of the referred to tasks are not included within the expenditure of the Programme:

• informing of the persons employed in State administration and the society regarding the basic principles of ethics in State administration (Task No. 32 of the Programme, which is related to that specified in the Guidelines for the State Administration Development Policy 2008-2013);

• introduction of the Construction Information System (CIS) (Task No. 53 of the Programme, Operational Strategy of the Ministry of Economics 2007-2009);

• to conduct professional training of the staff of law enforcement institutions and raising of qualification thereof in combating economic crimes and organised crime (Task No. 66 of the Programme, which conforms to that specified in the National Programme for the Prevention, Combating and Reduction of the Organised Crime 2006-2010);

• to simplify the procedures for fulfilment of customs and tax liabilities, to improve customer service and to reduce the direct and indirect costs of fulfilling the liabilities, concurrently ensuring the necessary control, using modern information technologies (Task No. 56 of the Programme, which conforms to the Development Strategy of the State Revenue Service 2007-2009).

In general the implementation of the Programme measures in 2009 and in subsequent years will be ensured within the scope of the funds allocated from the State budget. It is planned to update the Programme in 2011.

6. Procedure for Reporting and Evaluation

Introduction of the Programme shall be co-ordinated by the CPCB. The institutions involved in the fulfilment of the Programme shall, by 31 January of the current year (from 2010), submit information to the Corruption Prevention and Combating Bureau on execution of the tasks.

The CPCB shall, by 1 March 2014, submit an informative report to the Cabinet on the implementation of the National Guidelines for the Corruption Prevention and Combating 2010-2013 and the Programme.

# Footnotes

Each year the CPCB has gathered information regarding the fulfilment of the tasks from all institutions involved in the implementation of the Corruption Prevention and Combating Programme 2004-2008. The informative reports and reviews on the fulfilment of each task can be found on the CPCB home page.

Indicator of the control of corruption is one of six parameters of the international comparative indicator GRICS of the World Bank. GRICS (Governance Research Indicator Country Snapshot) is a complex indicator, which is prepared by the WBI once every two years and which consists of several hundred different variables accumulated from the information obtained by 18 different international organisations. More information regarding this indicator is available on the Internet home page of the WB: http://info.worldbank.org/governance/wgi/index.asp

The World Bank performs measurements of this indicator once every two years.

The indicator of the rule of law is one of six parameters of the international comparative indicator GRICS of the World Bank (see also reference No. 3)

Corruption perception index of the Transparency International

Forecast of the State Chancellery, according to the Guidelines for the Development of the State Administrative Policy 2008-2013